## Sheet1
Timetable Minor Project group 01
Core Project Document 10-Nov
Making the core dynamics of the game David, Rick & Laurens
David | Core gameplay lopen, schieten & acties | Health system, toggle weapons | Online Multiplayer
Rick | Building basic world | Bots | Bots
Laurens | assist gameplay | Bots | Bots
Making the 3D models and textures for the game Iris & Mats
Iris | 3D meshes Characters | 3D meshes Weapons | 3D animation
Mats | 3D meshes Characters | Start, pause and end screen. | Finishing UI
Prototyping Report 24-nov
Game Design Documents 27-nov
Extending the core dynamics of the game
|  |  | David | Online Multiplayer | Camera Shaker, Particle system. | Finishing touch
|  |  | Rick | Database | Database | &
|  |  | Laurens | Database or Multiplayer | Killcam, implementing audio | Delay
Making the environment
|  |  | Iris | 3D environment | 3D environment
|  |  | Mats | Gathering Audio | 3D environment
Early Access 18 December
(let the testers test the Early Access)
[7 empty] | CHRISTMAS | CHRISTMAS
Interpret the results from the testers
Deliverables
| Art Team | [7 empty] | Game analytics report 6 Januari
Programming team
Fix all the minor bugs for the programming team and details for the art team
Beta Release 15 Januari
| week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10
| 9-Nov -> 15-Nov | 16-Nov -> 22-Nov | 23-Nov -> 29-Nov | 30-Nov -> 5-Dec | 6-Dec -> 12-Dec | 13-Dec -> 19-Dec | 20-Dec -> 26-Dec | 27-Dec -> 3-Jan | 4-Jan -> 10-Jan | 11-Jan -> 17-Jan